## Audio Book Application
Pet Game website
|  | GANTT Chart : Audiobook Appilcation -Flutter (Mobile & Web) Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL08022022 <SCI.ID.> / Ver: 01.0 |  |  |  |  | Resources | Dev 1
Note: Non working days and , Holidays are not added in this chart.
[8 empty] | Project Start Date | 2022-03-07 |  | March | [27 empty] | April | [28 empty] | May | [30 empty] | June | [41 empty] | July | [41 empty] | August | [21 empty] | September
 | time axis 2022-03-07 to 2022-10-01
S# | Requirement ID | Task Description | Dev 2 (APIs Creation) | Milestone |  | Duration | Resource | Weekday Duration | Start | End | time axis 2022-03-07 to 2022-10-01
1 | BR001 | Designing of the web and Mobile pages (PNG format) > Sign up /login page > Forget password > Setting page on the right corner at the home page (Account section, Manage subscription plan, Notifications, about, T&C, Feedback, help center, Contact us ) > Home screen (books in pdf or audio form) - At the top user name - Filter based on search (Author, collection, Name of the PDF) - Subscription alert page for clicking on any audio/PDF format - While clicking on any PDF image will open below it options for choosing, Read now, Play now, add to the bookmark, add to Favorite icons will be shown. Below is about /summary text - Similar books options > Explore or search bar page - Searching by using filter (Title, author, topic) - Filter can be used based on categories > My library (List of the books and audio which User last opened which we used as a bookmark &add to favorite as well) | No API Task | MS-1 | Dev 2 | 0 | Dev 1 | 10 | 2022-03-07 | 2022-03-23 | bar: 2022-03-10 to 2022-03-11
2 | BR002 | Development & Functionalities (Mobile & Web) > Signup/login/Forgot password (Functionality for user ) - Project set up / server set up - Sign up page UI design and API impemantaion - Login page UI design and API implementation - Forgot Password page UI design API Implementation - Testing and Fixes | > API's creation with respect to the tasks given for BR002 | MS-2 |  | 4 | Dev 1 | 15 | 2022-03-24 | 2022-04-08
3 | BR003 | Development & Functionalities (Mobile & Web) > Home page (User profile functionalities) - User name at the top right corner UI design - listing of the books UI design API implemenation - Listing of the users - Setting icon - At the bottom of the app , bottom bar will be there on which we have three icons will be there- Home, search, My Library - Audio file name, image, description - Summary for the individual audio book for trail version - Format of the audio book (PDF or audio) - Setting icon (Clicking on will open the setting page on which different features will be shown) - Testing and fixes | >API's creation with respect to the tasks mentioned in BR003 | MS-3 | Dev 2 | 5 | Dev 1 | 10 | 2022-04-14 | 2022-04-24
4 | BR004 | Development & Functionalities (Mobile and Web) > Home page - Setting page UI design - Account setting for the users - Manage subscription plan for the users UI design - Terms and Conditions UI design - Feedback column for the users - Help centre details and its functional development - Contact us details UI design - Pagination and its validation - Testing and Fixes | >API's creation and implementiaon with respect to the tasks mentioned in BR004 | MS-4 | Dev 2 | 4 | Dev 1 | 11 | 2022-05-01 | 2022-05-12
5 | BR005 | Development & Functionality (Mobile and web) > Home page -Audio book features - Read audio book functionality - Play audio book functionality - Pause audio book functionality - add to the bookmark functionality API implementation - Add to favourite functionality API implementation - Read or play the audio book from where it paused - Blink features for each audio book - Summary /notes for each audiobook functionality -Similar book options features development - Testing and Fixes | >API's creation with respect to the tasks mentioned in BR005 | MS-5 | Dev 2 | 4 | Dev 1 | 10 | 2022-05-21 | 2022-06-02
6 | BR006 | Development and functionality(Mobile and web) > Audio book reading features - Speed control of the reading like 1X 2x - Book synchronization API implemantion - Sleep time Auto/off. - Testing and Fixes | >API's creation with respect to the tasks mentioned in BR006 | MS-6 | Dev 2 | 2 | Dev 1 | 14 | 2022-06-08 | 2022-06-24 | bar: 2022-06-19 to 2022-07-11
7 | BR007 | Development & Funcationality (Mobile and web) > Search page - API’s implementation for the search results based on any primary alphabets - Search results based on the filters (Author, Title, Topic) API implemenation - Filter search based on categories - Testing and fixes | API creation with respect to the tasks given in BROO7 | MS-7 | Dev 2 | 3 | Dev 1 | 12 | 2022-06-27 | 2022-07-08 | bar: 2022-07-07 to 2022-07-30
8 | BR008 | Development and Functionality (Mobile and web) > My Library - List of the Audio booksAPI implmention - Last played API implemention - Paused audio book functionality - List of the books added to the bookmark API implementation - List of the books added to the favourite API implemenation - Testing and fixes | >API creation with respect to the tasks given in BROO8 | MS-8 | Dev 2 | 2 | Dev 1 | 13 | 2022-07-14 | 2022-07-29 | bar: 2022-07-30 to 2022-08-15
9 | BR009 | Development and Functioanlity (Moible and Web) > Subscription Page - Subscription alert feature for reading or playing the audio book - Subscription plan for 1 year functionality (Radio button to choose) - Subscription page UI design and API implementation - Subscribe Now CTA button - Testing and fixes | > API's creation and its implementaion with respect to the tasks given for BR009 | MS-9 | Dev 2 | 3 | Dev 1 | 12 | 2022-08-02 | 2022-08-14 | bar: 2022-08-16 to 2022-09-01
10 | BR010 | Development and Functioanliy (Mobile and web) > Payment gateway - PayPal payment gateway integration - API implemenation - Payment gateway page - Merchant transactions - Debit/credit card details filling - Pay now - Testing and fixes | > API's creation task related to the BR010 | MS-10 | Dev 2 | 3 | Dev 1 | 13 | 2022-08-16 | 2022-08-29 | bar: 2022-09-23 to 2022-10-01
11 | BR011 | Development and Functionality (Mobile and web) > Miscellaneous work - Testing of the web and mobile app - Bug fixing - UAT - Project closure and deployment on the server |  | MS-11 |  |  | Dev 1 | 10 | 2022-09-02 | 2022-09-17
0
Holiday
[8 empty] | 2021-01-01 | 2021-01-01
[8 empty] | 2021-01-14 | 2021-01-14