## Audio book app Admin panel
Audio Book (Admin panel)
|  | GANTT Chart : Audio book app (Admin panel ) Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL04032022 <SCI.ID.> / Ver: 01.0 |  | Resources | Dev 1
Note: Only working days are considered in this gantt chart
[5 empty] | Project Start Date | 2022-03-07 |  | March | [27 empty] | April | [28 empty] | May | [30 empty] | June
 | time axis 2022-03-07 to 2022-08-31
S# | Requirement ID | Task Description | Milestone | Resource | Weekday Duration | Start | End | time axis 2022-03-07 to 2022-08-31
1 | BR001 | Design and Development > Admin panel design theme setup > Admin panel login page > Admin panel profile edit and display popup page > Admin panel user dashboard creation > Admin panel content management page > Admin panel advertisement management page > Admin panel Audio books management page > Admin panel Auto fund calculator page > Admin panel language converter | MS-1 | Dev 1 | 10 | 2022-03-07 | 2022-03-17 | bar: 2022-03-10 to 2022-03-11
2 | BR002 | Development & Functionalities > Admin panel user login API creation and implementation > Form validation > Admin panel edit profile API creation and implementation > Admin update profile name, image API creation and implementation > Testing and fixes | MS-2 | Dev 1 | 15 | 2022-03-18 | 2022-04-03
3 | BR003 | Development & Functionalities > Admin User management section - List of the users - Email id - Phone number - Subscription plan - Status of the subscription plan - Add/Edit/Delete feature for the particular user - Testing and fixes | MS-3 | Dev 1 | 15 | 2022-04-04 | 2022-04-20
4 | BR004 | Development & Functionalities > Admin Audio book management - Upload audio books - PDF/Audio file format - Name for the audio book - Highlights - Summary of the audio books - Amount to show for the each audio book - Testing and Fixes | MS-4 | Dev 1 | 15 | 2022-04-21 | 2022-05-06
5 | BR005 | Development & Functionalities > Admin panel content management - Frontend contents creation and upload - Contact us - About the app content - Notifications for the users - Testing and fixes | MS-5 | Dev 1 | 15 | 2022-05-07 | 2022-05-23
6 | BR006 | Development & Functionality > Admin panel Subscription plan management - New plan creation - Price setup for the subscription plans on the basis of the days and months - Offline plans for the audio books - Subscription alert request - Subscription plan valid date - Testing and fixes | MS-6 | Dev 1 | 15 | 2022-05-24 | 2022-06-10
7 | BR007 | Development & Functionality > Admin panel extra content management - Extra contents text creations - New photos addition - Social media integration - Testing and fixes | MS-7 | Dev 1 | 15 | 2022-06-11 | 2022-06-26
0
Holiday
[5 empty] | 2021-01-01 | 2021-01-01
[5 empty] | 2021-01-14 | 2021-01-14