## Gantt Chart
|  | GANTT Chart : Hiferr Mobile app (Android) Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL07292022 <SCI.ID.> / Ver: 01.0 |  | Resources | Dev 1
Dev2
|  | Note: Non- working days/public holdiays are not consider in this Gantt chart |  |  | Project Start Date | 2022-08-03 |  | August | [56 empty] | September | [30 empty] | October | [29 empty] | November | [30 empty] | December | [28 empty] | January | [29 empty] | February | [30 empty] | March | [29 empty] | April
 | time axis 2022-08-03 to 2023-05-29
S# | Requirement ID | Task Description | Milestone | Resource | Weekday Duration | Start | End | time axis 2022-08-03 to 2023-05-29
1 | BR001 | > UI/UX development In PNG (Both android and Ios) - Splash screen - Phone number enter screen - OTP screen for verification of the number - Sign up page - - Meet screen - Create meet & Profile page - Add profile & pics with multiple profile - Open dropdown page - Add and create keywords - Add religion dropdown - Status dropdown - Ethnic background - Qualification - Current location with profile data - List of meet people - List fetch with profile location - Search profiles - Skills - Show profile detail with search results highlights match keyword - Give option to msg user - Create filter - Add filter data source - Matched profile with filter data source - Show profile according to filter - Profile page (Account setting, Profile icon image edit and change, email , phone number, toggle on/off for message and notifications, delete your account, invite friends , app version info at the bottom, unblock the blocked user) - Flash screen page with features - Chat page ( list of chat user’s , search chat , chat notification , clicking on any chat will open chat box, last seen - - Profile page (Account setting, Profile icon image edit and change, email , phone number, toggle on/off for message and notifications, delete your account, invite friends , app version info at the bottom, unblock the blocked user) - Chat page ( list of chat user’s , search chat , chat notification , clicking on any chat will open chat box, last seen) - Internal testing and fixes | UI | Dev 1 | 5 | 2022-08-03 | 2022-08-10
2 | BR002 | > Development & Functionality (Android ) - XML design of the splash screen, sign up , Phone number to login , OTP verification screen - Sign up and its implementation - Phone number SMS Key API integration - Internal testing and fixes | MS-1 | Dev 1 | 5 | 2022-08-16 | 2022-08-23
3 | BR003 | > Development & Functionality (Android ) - Meet screen XML design and features development - Create meet & Profile page - Add profile & pics with multiple profile - Open dropdown page - Add and create keywords - Add religion dropdown - Status dropdown - Ethnic background - Qualification - Current location with profile data - List of meet people - List fetch with profile location - Internal testing and fixes | MS-2 | Dev 1 | 10 | 2022-08-24 | 2022-09-06
4 | BR004 | > Development and Functionality (Android) - Search profile in meet section development on the basis of keywords - Skills - Show profile detail with search results highlights match keyword - Give option to msg user - Internal testing and fixes | MS-3 | Dev 1 | 10 | 2022-09-07 | 2022-09-20
5 | BR005 | > Development & Functionality (Android) - Create filter - Add filter data source - Matched profile with filter data source - Show profile according to filter - Internal testing and fixes | MS-4 | Dev 1 | 10 | 2022-09-21 | 2022-10-04
6 | BR006 | > Development & Functionality (Android) - Profile page development (All the features such as profile edit, notification toggle, app version, unblock the block users , T& C Privacy policy etc) - Flash screen development in XML as per the features - Latest status comes on top with date and time for every status - Flash features complete development - Internal testing and fixes | MS-5 | Dev 1 | 10 | 2022-10-06 | 2022-10-19
7 | BR007 | > Development & Functionality (Android) - Chat screen development in XML as per the features - Real time chat integration through firebase - Last seen , online user - Read /unread messages etc. - Internal testing and fixes - Notification functionality though firebase - All the live notifications splashes - Other features - Internal testing and fixes - UAT - Finalization of the app | MS-6 | Dev 1 | 10 | 2022-10-20 | 2022-11-07
Holiday
2022-05-03
2022-07-10
2022-07-11
2022-08-09
2022-08-11
2022-08-15
2022-08-19
2022-10-02
2022-10-05
2022-10-24
2022-10-25
2022-10-26
2023-01-01
2023-01-15
2023-01-26
2023-03-07
2023-03-08