## Gantt Chart
|  | GANTT Chart : Social Mobile app (Web Admin panel) Release ID: Augurs Tech: Protected Controlled Copy Project ID: ATPL07292022 <SCI.ID.> / Ver: 01.0 |  | Resources | Dev 1
Dev 2
|  | Note: Non- working days/public holdiays are not consider in this Gantt chart |  |  | Project Start Date | 2022-08-03 |  | August | [56 empty] | September | [30 empty] | October | [29 empty] | November | [30 empty] | December | [28 empty] | January | [29 empty] | February | [30 empty] | March | [29 empty] | April
 | time axis 2022-08-03 to 2023-05-29
S# | Requirement ID | Task Description | Milestone | Resource | Weekday Duration | Start | End | time axis 2022-08-03 to 2023-05-29
1 | BR001 | > Theme finalization (Checked by client) > Theme set up (All static pages ) > Admin login page > Admin log out page > Dashboard > User management > User log > Filter management > Create user > Internal testing and fixes | MS-1 | Dev 1 | 10 | 2022-08-03 | 2022-08-22
2 | BR002 | > Login for admin > Log for admin > Dashboard features ( Such as total users. Active users) > User management (Such as list of all the registered user as per their details on the mobile app entered, edit user, delete user, view user details) > Internal testing and fixes | MS-2 | Dev 1 | 10 | 2022-08-23 | 2022-09-05
3 | BR003 | > User log management features development > User details > Last login > Active users > Offline users > Export user details > Internal testing and fixes | MS-3 | Dev 1 | 10 | 2022-09-06 | 2022-09-19
4 | BR004 | > Create user functionality > Add name > Add email id > Phone number > Change login details of the existing users > Internal testing and fixes > UAT | MS-4 | Dev 1 | 10 | 2022-09-20 | 2022-10-03
Holiday
2022-05-03
2022-07-10
2022-07-11
2022-08-09
2022-08-11
2022-08-15
2022-08-19
2022-10-02
2022-10-05
2022-10-24
2022-10-25
2022-10-26
2023-01-01
2023-01-15
2023-01-26
2023-03-07
2023-03-08