## Zetwal Music App (Web admin)
Zetwal Music App (Web admin panel)
|  | GANTT Chart : Zetwal Music app (Web Admin panel) Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL08082022 <SCI.ID.> / Ver: 01.0 |  |  | Resources |  | Dev 1
[7 empty] | Project Start Date | 2022-08-16 |  | August | [20 empty] | September | [35 empty] | October | [30 empty] | November | [21 empty] | September | [22 empty] | October
 | time axis 2022-08-16 to 2023-02-09
S# | Requirement ID | Task Description | Milestone | Resource | Resrouce | Weekday Duration | Weekday Duration | Start | End | time axis 2022-08-16 to 2023-02-09
1 | BR001 | > Theme finalization (Static pages ) > Theme set up > Admin login page > Admin log out page > Dashboard (like total users, active users, Lyricist, composers in numbers only) > User management > Any other admin pages (If any) > Internal testing and fixes | MS-1 | Dev 1 |  |  | 15 | 2022-08-16 | 2022-09-05 | bar: 2022-08-19 to 2022-08-20
2 | BR002 | > User Management development - List of users joined the app - Name of the users - Email id - Country details - Status (Singer, lyricists, Musician, composer etc.) - View user Contents (If public) - Active/Inactive user - Internal testing and fixes | MS-2 | Dev 1 |  |  | 15 | 2022-09-06 | 2022-09-26
3 | BR003 | > Create users - Admin will create users - Form creation for creating user - Fill details like name, email id , country, status, Image upload - Internal testing and fixes | MS-3 | Dev 1 |  |  | 10 | 2022-09-27 | 2022-10-11
4 | BR004 | > Admin Profile edit - Edit name - Edit profile pic - Update profile - Logout from the admin section - Internal testing and fixes - UAT - Project handover | MS-4 | Dev 1 |  |  | 15 | 2022-10-12 | 2022-11-01
0
Holiday
[7 empty] | 2021-01-01 | 2021-01-01
[7 empty] | 2021-01-14 | 2021-01-14