## Zetwal Mobile app (ios)
Zetwal Mobile App (ios)
|  | GANTT Chart : Zetwal Mobile app (ios) Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL08042022 <SCI.ID.> / Ver: 01.0 |  |  | Resources |  | Dev 1
[7 empty] | Project Start Date | 2022-08-16 |  | August | [20 empty] | September | [35 empty] | October | [30 empty] | November | [21 empty] | September | [22 empty] | October
 | time axis 2022-08-16 to 2023-02-09
S# | Requirement ID | Task Description | Milestone | Resource | Resrouce | Weekday Duration | Weekday Duration | Start | End | time axis 2022-08-16 to 2023-02-09
1 | BR001 | > Development & Functionality - XML design of the splash screen, sign up and login page - XML design for forget password, reset password, logout page - Sign up & login API creation and its implementation - Forget Password & Logout API creation and its implementations - Internal testing and fixes | MS-1 | Dev 1 |  | 12 |  | 2022-08-16 | 2022-08-31 | bar: 2022-08-19 to 2022-08-20
2 | BR002 | > Development & Functionality - Home page XML designs ( Search bar, few random profiles, bottom bar will have home icon, Profile, chat , Notification icon) - Profile page of the user XML design - Edit / update Profile API creation and its implementation - Edit profile will have the features for edit or upload profile picture from camera or gallery of the phone, edit Name , edit Status from the dropdown - Internal testing and fixes | MS-2 | Dev 1 |  | 10 |  | 2022-09-01 | 2022-09-14
3 | BR003 | > User Profile page development (Personal account) - Tell everyone about Yourself title and below it a Box in which user can add his contents in the text form - Attachment icon – User can attach any video , files from his device by clicking on the attachment icon Any files , media, clips - Any link pasted in the box. - Public and Private button to post the content (If chosen public it will display to other users if private it will keep private only display to the user privately ) - Internal testing and fixes | MS-3 | Dev 1 |  | 10 |  | 2022-09-15 | 2022-09-28
4 | BR004 | Development & Functionality > Search bar features - User can search any profile by entering the keywords typed in the search box - Display the results of the searched users below on the home page - Choose any of the user profile by clicking on it - XML page design for the View profile of the other users details like Image of the users, name, status, about theirseleves, recent posts (If public). - Internal testing and fixes | MS-4 |  |  | 10 |  | 2022-09-29 | 2022-10-12 | bar: 2022-09-29 to 2022-10-09
5 | BR005 | Development & Functionality > Chat & Notification Features development - Firebase set up for real time chat - Chat page Development in XML - Search bar for searching chats - Recent chats of the users - Search user for chat and redirection of the users in the chat window for chat. - Notifications through firebase - Internal testing and fixes | MS-5 |  |  | 10 |  | 2022-10-13 | 2022-10-31 | bar: 2022-10-10 to 2022-10-31
6 | BR006 | Development & Functionality > Profile page (Others Account) - View profile of the users - View recent posts (If public) - Request for chat with the user whose profile viewed by other user. - Click on any link posted redirect the user towards that page , open recorded clips posted in the app (Play/ Pause) - Internal testing and fixes | MS-6 |  |  | 10 |  | 2022-11-01 | 2022-11-14 | bar: 2022-11-01 to 2022-11-14
7 | BR007 | Development & Functionality - Testing of the complete app - UAT - Fixes /Suggestions (If any) - Finalization of the app | MS-7 | Dev 1 |  | 13 |  | 2022-11-15 | 2022-12-01
0
Holiday
[7 empty] | 2021-01-01 | 2021-01-01
[7 empty] | 2021-01-14 | 2021-01-14